## Fix First
# | What's wrong | The fix | Effort | Metric unblocked
1 | 35% of active inventory has no occasion text (DB: 281/434 active products have styling_metadata.occasion). The occasion stylist — the entire wedge — is invisible to a third of the catalog, so even a perfect occasion prompt returns thin picks. | Run the existing enrich-occasions edge fn in backfill mode (POST {backfill:N}) over the ~153 products with empty occasion text. Pure data job, zero code. | S | Activation + conversion
2 | Occasion text isn't in the consumer search ranker. search_products' BM25 tsvector weights name/brand/type/description only (migration 20260602000003 L81-93) — the occasion field the enrichment engine writes is not indexed. A shopper typing "wedding guest" only matches literal name/description text. | One setweight line in a new migration adding occasion (+material/keywords) to the tsvector. Compounds directly with fix #1 (fills the field it indexes). | S | Activation + conversion
3 | Veo try-on fallback silently renders the WRONG outfit. On Seedance submit-fail the product-blind Veo fallback marks status='done' while animating the selfie's original clothes and dropping the user's picks (~10%). A confidently-wrong try-on is worse than none — it destroys the trust the loop runs on. | The guard is already written (generate-look/index.ts L520-522 allowProductBlindFallback, L770-795 gate). Confirm app_settings.look_video_fallback='false', make failure loud (retry prompt, not silent done), and add an alert if the dial is ever ON with products present. | S | Activation + trust
4 | Fake price-comparison chips. buildRetailerOffers (ProductPage.tsx L175) invents 3 alt-retailer chips with hash-jittered prices pointing at generic search URLs (amazon.com/s?k=...) plus a fabricated "lowest/discount %" badge. Tapping the "cheapest" lands on a keyword search page, not the product — deceptive, and it burns ~75% of Shop taps. | Delete the ALT_RETAILERS loop + badge. Keep only the real product.url chip (already routes through the affiliate chokepoint). One-file removal. | S | Conversion + trust
5 | Seeding engine is OFF (seeding_enabled='false', never run in prod); 127 approved + 37 pending seed_targets sit idle. Catalog is thin (504 products, ~all <2mo old) — the supply side of the marketplace has no inflow. | Decide, don't leave half-alive: turn it on and watch it (it's the self-healing supply fix — the pipeline already exists), or freeze it and stop carrying idle surface. Given thin catalog is a wedge constraint, turn it on behind a rate cap. | M | Supply
6 | Shopify sync produces dead rows. All 28 synced Shopify products are structurally inactive (sync routes push rows through the URL scraper → fail → is_platform=false). Brands table = 4 rows. | Either fix the sync path so synced products land active/curatable, or stop syncing and don't ship inactive inventory. Low priority vs #1-4 (no real brand supply yet), but don't let dead rows accumulate. | M | Supply
7 | No funnel instrumentation. Bookmarks are localStorage-only (useBookmarks.ts — zero Supabase), so the strongest low-friction intent signal a shopper gives is thrown away server-side. No retention cohort computable, no saved-intent signal. | Add a saved_items table; mirror the existing toggle writes to it (keep localStorage as offline cache). No UI change. This is the prerequisite for any future re-engagement and is itself the signal to instrument. | S | Retention + conversion (instrumentation)
Effort: S = small (<1 day) · M = medium (days) · L = large

## Improve
Feature | Improvement | Effort | Metric
StyleUp chat (activation wall #1) | The empty composer is a passive "Say hi…" hint — the first keystroke is the biggest first-session drop. Seed the already-existing quickChips() renderer (StyleUpExperience.tsx L1819) for messages.length===0 with 4-6 one-tap occasion chips ("Date night", "Wedding guest", "Work week", "A trip"). Chip UI + send handler already exist; only the empty-state branch opts out. | S | Activation
StyleUp selfie (activation wall #2) | The selfie that unlocks "see it on me" is buried in a collapsible context-card editor (L1419-1443); a new user reaches the render before being told to add it. Front-load the photo ask on first thread entry. Reuses pickPhoto / uploadUserPhoto — just reorder when the ask appears. (Doppl dropped to one selfie precisely because full-body was the #1 abandonment point.) | M | Activation
ProductPage social proof | dummySavedBy (L237) fabricates "Saved by N shoppers" (47-527). Once saved_items exists (fix #7), back it with a real COUNT(*); if the real count is ~0, delete the module rather than lie. Folds into the fake-UI cleanup with #4. | S | Trust
Build-a-Catalog filters | composeFilterQuery drops price/budget entirely and mashes occasion+type+vibe into one bag-of-words string. Pass the price chip through as a structured filter_price predicate on search_products (the RPC already filters gender). Defer behind #1-2 — it's a secondary entry the wedge doesn't depend on. | S | Conversion
Recent-occasion re-entry | recordRecentSearch already populates a store; render it as tappable rows in the BottomBar search sheet so a returning shopper re-enters "wedding guest" in one tap. Defer — helps session 2+, and session 2 barely exists yet. | S | Retention (later)
Effort: S = small (<1 day) · M = medium (days) · L = large